## HKN ST-B4 Daily Report
Operations Integrity Management System
Document Title: SWT Daily Activity Report Document Code: OS-HOSWT-R003
[6 empty] | Rev No. V01 |  |  |  | Revision Date: 13-Sep-2015 |  |  | Page 1 of 1
6
Attention : |  | Mohammed Batati |  | Client : | HKN |  | Date : | 2021-09-12 |  |  |  | Client Logo:
From : |  | Bashar Mustafa |  | Field : | Swara Tika |  | Run : | N/A
cc : |  | Ari Azad, Emad & Ibrahim F. |  | Well : | ST-B4 |  | Job No : | KIU-SWT-HKNI-C-35849
OPERATION INFORMATION
|  |  |  | Y | N | Company | [6 empty] | Y | N
Security |  |  |  | Y |  | Mando |  |  | Personnel issues ? |  |  |  |  | N
MWD |  |  |  | Y |  | SLB |  |  | Job Planning ? |  |  |  | Y
Rig Services |  |  |  | Y |  | PD, Rig T-63 |  |  | Require equipment / supplies ? |  |  |  | Y
WL/ Slick Line |  |  |  | Y |  | Almansoori
Cementing |  |  |  | Y |  | OilServ |  |  | Transport issues ? |  |  |  |  | N
H2S Services |  |  |  | Y |  | AL MURABIT |  |  | Safety issues ? |  |  |  |  | N
Packer Services |  |  |  | Y |  | Packer Plus |  |  | Rising problems |  |  |  |  | N
Well Test |  |  |  | Y |  | OilServ |  |  | Miscellaneous |  |  |  |  | N
Mud Engineer |  |  |  | Y |  | PPC
Mud Logging |  |  |  | Y |  | Petro Service
Camp Services |  |  |  | Y |  | HKN
ADDITIONAL COMMENTS ON ABOVE |  |  |  |  | OSCAR EVENTS |  |  | WELL TESTING DATA FROM 06:00 TO 06:00
[8 empty] | Well Name |  |  |  |  | ST-B4
[8 empty] | Flowing hrs. |  |  |  |  | 0:00 |  | hrs
[8 empty] | Max. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Max. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Gas Rate Last 24 Hrs. | [6 empty] | MMscf/d
[8 empty] | Static pressure | [6 empty] | psi
[8 empty] | Diff pressure (Barton range ) | [6 empty] | 'H2O
CMF applied
[8 empty] | Total shipment( burned through burner) | [6 empty] | bbls
[8 empty] | Max. H2S recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Max. CO2 recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Avrg. BSW recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | MAX. WHP | [6 empty] | psi
[8 empty] | Max WHT | [6 empty] | deg C
Choke size / Pump RPM
EQUIPMENT & SPARE REQUIREMENTS | [7 empty] | COMPETITION SERVICE COMPANIES ACTIVITIES
Part No. |  |  | Description |  |  |  | Qty. | Serv. Company Name |  |  | Activity For last 24 Hrs.
1 | sampling bottles |  | IATA CAN I, 5 liters 40 + 25 and 1 liters plastic bottles 120 ea. |  |  |  |  | Al Mansori |  |  | Al Masori SL POOH tubing plug after two times wire cut, fishing operation completed.
2 | Apoxy |  | a poxy for welding non metal things. |  |  |  | 1
3 | buttery Fly valves |  | Require buttery fly valves to replace leaking air manifold valves |  |  |  | 3
4 | Heat sensor |  | for indirect heater |  |  |  | 1
5 | Side glass with valves. |  | Required water side glass with its isolation valves |  |  |  | 1 set
6 | Spill kit |  | Required Spill kit with its elements (Full). |  |  |  | 1
7 | Eye wash stand. |  | Eye wash stand |  |  |  | 1
8 | Ignition Cable |  | for Burner Oil line and one spare |  |  |  | 2
9 | 1/2" hose |  | 1/2" hose rated pressure more than 150 psi for drain system |  |  |  | 30 meter
10 | 3" 602 pipes & Elbow |  | 25 meter 3" 602 & 8 ea 90 elbow, 2 ea 45 Elbow
11 | Battery |  | for Baton, and AA size |  |  |  | 2 ea
12 | CO2 Tube |  | range 0.1 to 6 % |  |  |  | 3
CREW LIST
DAY SHIFT | [7 empty] | NIGHT SHIFT
Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION | Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION
Bashar Mustafa |  | 75 | 17 | 17 | [10 empty] | Night In-charge
|  | 50 | [12 empty] | TDA
Yassir Essam |  |  | 33 | 23 | [10 empty] | Chief Op.
Operator
|  | 50 | [12 empty] | Operator
45
|  | 90 | [7 empty] | 35
ACTIVITIES LAST 24 HRS
Indirect heater required heat sensor , used 2nd one for its temperature control.
SLB WL logging operation completed.
RIH lower completion in progress.
ACTIVITIES NEXT 24 HRS
complete RIH lower completion.
RIH production completion.
Prepared BY: Mohammed S. Albatati | [5 empty] | Reviewed By: Ahmad Ullah | [5 empty] | Approved By: Jean Luc Roudil
Revision No.: V01 | [5 empty] | Issued Date: 13-Sep-2015 | [5 empty] | Controlled Copy Online
|  |  | Name - Day Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Bashar Mustafa |  |  |  | 2021-08-27 | 2021-08-27 |  | 2021-09-24
|  |  | Mohammed Taha Hlawet |  |  |  | 2021-08-13 | 2021-08-21 |  | 2021-09-17
|  |  | Yassir Essam |  |  |  | 2021-08-11 | 2021-08-21 |  | 2021-09-08
|  |  | Barzan Jalal |  |  |  | 2021-08-24 | 2021-08-24 |  | 2021-09-21
|  |  | Waleed Khedir |  |  |  | 2021-08-20 | 2021-08-21 |  | 2021-09-17
|  |  | Name - Night Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Hawal Saleh |  |  |  | 2021-08-21 | 2021-08-21 |  | 2021-09-18
|  |  | Mohammed Sabri |  |  |  | 2021-08-25 | 2021-08-25 |  | 2021-09-22
|  |  | Mohammed Nuraddin |  |  |  | 2021-08-11 | 2021-08-21 |  | 2021-09-08
|  |  | Karokh Hazim |  |  |  | 2021-08-24 | 2021-08-24 |  | 2021-09-21
|  |  | Amanj Othman |  |  |  | 2021-08-20 | 2021-08-21 |  | 2021-09-17
Formulas:
Revision Date: 13-Sep-2015 = [Date :]+28

## Sheet1 (hidden)
Description | Qty.
Rain coat | 5
electric cable for lab cabin one piece 200 m | 1
Printer | 1
Torch light | 2
Fire extinguisher inspected and ready | 5
Pressure sensor | 2
Grounding Bar (Rod) | 4
Radio for communications | 5
better fly valve 6" | 3