## HKN ST-B4 Daily Report
Operations Integrity Management System
Document Title: SWT Daily Activity Report Document Code: OS-HOSWT-R003
[6 empty] | Rev No. V01 |  |  |  | Revision Date: 13-Sep-2015 |  |  | Page 1 of 1
6
Attention : |  | Mohammed Batati |  | Client : | HKN |  | Date : | 2021-09-13 |  |  |  | Client Logo:
From : |  | Bashar Mustafa |  | Field : | Swara Tika |  | Run : | N/A
cc : |  | Ari Azad, Emad & Ibrahim F. |  | Well : | ST-B4 |  | Job No : | KIU-SWT-HKNI-C-35849
OPERATION INFORMATION
|  |  |  | Y | N | Company | [6 empty] | Y | N
Security |  |  |  | Y |  | Mando |  |  | Personnel issues ? |  |  |  |  | N
MWD |  |  |  | Y |  | SLB |  |  | Job Planning ? |  |  |  | Y
Rig Services |  |  |  | Y |  | PD, Rig T-63 |  |  | Require equipment / supplies ? |  |  |  | Y
WL/ Slick Line |  |  |  | Y |  | Almansoori
Cementing |  |  |  | Y |  | OilServ |  |  | Transport issues ? |  |  |  |  | N
H2S Services |  |  |  | Y |  | AL MURABIT |  |  | Safety issues ? |  |  |  |  | N
Packer Services |  |  |  | Y |  | Packer Plus |  |  | Rising problems |  |  |  |  | N
Well Test |  |  |  | Y |  | OilServ |  |  | Miscellaneous |  |  |  |  | N
Mud Engineer |  |  |  | Y |  | PPC
Mud Logging |  |  |  | Y |  | Petro Service
Camp Services |  |  |  | Y |  | HKN
ADDITIONAL COMMENTS ON ABOVE |  |  |  |  | OSCAR EVENTS |  |  | WELL TESTING DATA FROM 06:00 TO 06:00
[8 empty] | Well Name |  |  |  |  | ST-B4
[8 empty] | Flowing hrs. |  |  |  |  | 0:00 |  | hrs
[8 empty] | Max. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Max. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Gas Rate Last 24 Hrs. | [6 empty] | MMscf/d
[8 empty] | Static pressure | [6 empty] | psi
[8 empty] | Diff pressure (Barton range ) | [6 empty] | 'H2O
CMF applied
[8 empty] | Total shipment( burned through burner) | [6 empty] | bbls
[8 empty] | Max. H2S recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Max. CO2 recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Avrg. BSW recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | MAX. WHP | [6 empty] | psi
[8 empty] | Max WHT | [6 empty] | deg C
Choke size / Pump RPM
EQUIPMENT & SPARE REQUIREMENTS | [7 empty] | COMPETITION SERVICE COMPANIES ACTIVITIES
Part No. |  |  | Description |  |  |  | Qty. | Serv. Company Name |  |  | Activity For last 24 Hrs.
1 | sampling bottles |  | IATA CAN I, 5 liters 40 + 25 and 1 liters plastic bottles 120 ea. |  |  |  |  | Al Mansori |  |  | Al Masori SL POOH tubing plug after two times wire cut, fishing operation completed.
2 | Apoxy |  | a poxy for welding non metal things. |  |  |  | 1
3 | buttery Fly valves |  | Require buttery fly valves to replace leaking air manifold valves |  |  |  | 3
4 | Heat sensor |  | for indirect heater |  |  |  | 1
5 | Side glass with valves. |  | Required water side glass with its isolation valves |  |  |  | 1 set
6 | Spill kit |  | Required Spill kit with its elements (Full). |  |  |  | 1
7 | Eye wash stand. |  | Eye wash stand |  |  |  | 1
8 | Ignition Cable |  | for Burner Oil line and one spare |  |  |  | 2
9 | 1/2" hose |  | 1/2" hose rated pressure more than 150 psi for drain system |  |  |  | 30 meter
10 | 3" 602 pipes & Elbow |  | 25 meter 3" 602 & 8 ea 90 elbow, 2 ea 45 Elbow
11 | Battery |  | for Baton, and AA size |  |  |  | 2 ea
12 | CO2 Tube |  | range 0.1 to 6 % |  |  |  | 3
CREW LIST
DAY SHIFT | [7 empty] | NIGHT SHIFT
Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION | Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION
Bashar Mustafa |  | 75 | 18 | 18 |  | 2021-10-01 | SWT Supervisor | Hawal Salh |  |  | 1 | 1 |  | 2021-10-11 | Night In-charge
Ghamdan Abdulqader |  | 50 | 1 | 1 |  | 2021-10-18 | TDA | Muhamad Sabri |  |  | 1 | 1 |  | 2021-10-11 | TDA
Yaser Essam |  |  | 34 | 24 |  | 2021-09-15 | Chief Op. | Revan Andraw |  |  | 1 | 1 |  | 2021-10-11 | Chief Op.
Gailan Rahim |  |  | 1 | 1 |  | 2021-10-18 | Operator | Amanj Othman |  |  | 1 | 1 |  | Consultant | Operator
Barzan Jalal |  | 50 | 1 | 1 |  | Consultant | Operator | Karohk Hazem | [5 empty] | Consultant | Operator
45
|  | 90 | [7 empty] | 35
ACTIVITIES LAST 24 HRS
Indirect heater required heat sensor , used 2nd one for its temperature control.
RIH lower completion almost completed.
Plan to complete STB3 production completion and Xmass tree. than rig up SWT piping for bleed off after CT open SSD 9 and SL install memory gauges. Than move to STB4.
Testing Crew will back today.
Air compressors needs tomorrow to rigup and function test.
ACTIVITIES NEXT 24 HRS
complete RIH lower completion.
RIH production completion.
Prepared BY: Mohammed S. Albatati | [5 empty] | Reviewed By: Ahmad Ullah | [5 empty] | Approved By: Jean Luc Roudil
Revision No.: V01 | [5 empty] | Issued Date: 13-Sep-2015 | [5 empty] | Controlled Copy Online
|  |  | Name - Day Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Bashar Mustafa |  |  |  | 2021-08-27 | 2021-08-27
|  |  | Ghamdan Abdulqader |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Yaser Essam |  |  |  | 2021-08-11 | 2021-08-21
|  |  | Gailan Rahim |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Barzan Jalal |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Name - Night Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Hawal Salh |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Muhamad Sabri |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Revan Andraw |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Amanj Othman |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Karohk Hazem |  |  |  | 2021-09-13 | 2021-09-13

## Sheet1 (hidden)
Description | Qty.
Rain coat | 5
electric cable for lab cabin one piece 200 m | 1
Printer | 1
Torch light | 2
Fire extinguisher inspected and ready | 5
Pressure sensor | 2
Grounding Bar (Rod) | 4
Radio for communications | 5
better fly valve 6" | 3