## HKN ST-B4 Daily Report
Operations Integrity Management System
Document Title: SWT Daily Activity Report Document Code: OS-HOSWT-R003
[6 empty] | Rev No. V01 |  |  |  | Revision Date: 13-Sep-2015 |  |  | Page 1 of 1
6
Attention : |  | Mohammed Batati |  | Client : | HKN |  | Date : | 2021-09-15 |  |  |  | Client Logo:
From : |  | Bashar Mustafa |  | Field : | Swara Tika |  | Run : | N/A
cc : |  | Ari Azad, Emad & Ibrahim F. |  | Well : | ST-B4 |  | Job No : | KIU-SWT-HKNI-C-35849
OPERATION INFORMATION
|  |  |  | Y | N | Company | [6 empty] | Y | N
Security |  |  |  | Y |  | Mando |  |  | Personnel issues ? |  |  |  |  | N
MWD |  |  |  | Y |  | SLB |  |  | Job Planning ? |  |  |  | Y
Rig Services |  |  |  | Y |  | PD, Rig T-63 |  |  | Require equipment / supplies ? |  |  |  | Y
WL/ Slick Line |  |  |  | Y |  | Almansoori
Cementing |  |  |  | Y |  | OilServ |  |  | Transport issues ? |  |  |  |  | N
H2S Services |  |  |  | Y |  | AL MURABIT |  |  | Safety issues ? |  |  |  |  | N
Packer Services |  |  |  | Y |  | Packer Plus |  |  | Rising problems |  |  |  |  | N
Well Test |  |  |  | Y |  | OilServ |  |  | Miscellaneous |  |  |  |  | N
Mud Engineer |  |  |  | Y |  | PPC
Mud Logging |  |  |  | Y |  | Petro Service
Camp Services |  |  |  | Y |  | HKN
ADDITIONAL COMMENTS ON ABOVE |  |  |  |  | OSCAR EVENTS |  |  | WELL TESTING DATA FROM 06:00 TO 06:00
[8 empty] | Well Name |  |  |  |  | ST-B4
[8 empty] | Flowing hrs. |  |  |  |  | 0:00 |  | hrs
[8 empty] | Max. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Max. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[8 empty] | Avrg. Gas Rate Last 24 Hrs. | [6 empty] | MMscf/d
[8 empty] | Static pressure | [6 empty] | psi
[8 empty] | Diff pressure (Barton range ) | [6 empty] | 'H2O
CMF applied
[8 empty] | Total shipment( burned through burner) | [6 empty] | bbls
[8 empty] | Max. H2S recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Max. CO2 recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | Avrg. BSW recorded Last 24 Hrs. | [6 empty] | %
[8 empty] | MAX. WHP | [6 empty] | psi
[8 empty] | Max WHT | [6 empty] | deg C
Choke size / Pump RPM
EQUIPMENT & SPARE REQUIREMENTS | [7 empty] | COMPETITION SERVICE COMPANIES ACTIVITIES
Part No. |  |  | Description |  |  |  | Qty. | Serv. Company Name |  |  | Activity For last 24 Hrs.
1 | Side glass with valves. |  | Required water side glass with its isolation valves |  |  |  | 1 set | Al Mansori |  |  | Al Masori SL POOH tubing plug after two times wire cut, fishing operation completed.
2 | Eye wash stand. |  | Eye wash stand |  |  |  | 1
3 | Ignition Cable |  | for Burner Oil line and one spare |  |  |  | 2
4 | TDA Sensors |  | pressure & Temperature |  |  |  | 1 + 2
5 | TDA Battery |  | TDA battery for sensors |  |  |  | 3
6 | 1 liter plastic bottles |  | Required 50 ea 1 liter plastic bottles. |  |  |  | 50
7
8
9
10
11
12
CREW LIST
DAY SHIFT | [7 empty] | NIGHT SHIFT
Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION | Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION
Bashar Mustafa |  | 75 | 20 | 20 |  | 2021-10-01 | SWT Supervisor | Hawal Salh |  |  | 1 | 1 |  | 2021-10-11 | Night In-charge
Ghamdan Abdulqader |  | 50 | 3 | 3 |  | 2021-10-18 | TDA | Muhamad Sabri |  |  | 1 | 1 |  | 2021-10-11 | TDA
Yaser Essam |  |  | 36 | 26 |  | 2021-09-15 | Chief Op. | Gailan Rahim |  |  | 1 | 1 |  | 2021-10-11 | Chief Op.
Dolovan Khalid |  |  | 3 | 3 |  | 2021-10-18 | Operator | Amanj Othman |  |  | 1 | 1 |  | Consultant | Operator
Barzan Jalal |  | 50 | 3 | 3 |  | Consultant | Operator | Karohk Hazem |  |  | 1 | 1 |  | Consultant | Operator
45
|  | 90 | [7 empty] | 35
ACTIVITIES LAST 24 HRS
RIH 4 1/2" tubing completed.
Al Mansori SL RIH prong plug, Tubing & SCSSV pressure tested ok. Plugs retrieved.
Rig BOP removed, installing Production Xmass tree in progress.
4 ea Atlas copco air compressors received with hoses , rig up ok.
Air compressors PT & function test done.
STB4 Rig BOP removed and installing Xmass tree in going.
CT spot of equipment, preparation for rig up.
ACTIVITIES NEXT 24 HRS
Rig up to STB3 for PT and Bleed of CT & SL (open SSD 9, Set EMR).
Move to STB4.
RIH production completion.
Prepared BY: Mohammed S. Albatati | [5 empty] | Reviewed By: Ahmad Ullah | [5 empty] | Approved By: Jean Luc Roudil
Revision No.: V01 | [5 empty] | Issued Date: 13-Sep-2015 | [5 empty] | Controlled Copy Online
|  |  | Name - Day Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Bashar Mustafa |  |  |  | 2021-08-27 | 2021-08-27
|  |  | Ghamdan Abdulqader |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Yaser Essam |  |  |  | 2021-08-11 | 2021-08-21
|  |  | Dolovan Khalid |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Barzan Jalal |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Name - Night Shift |  |  |  | Arrival Date | On location |  | Out location
|  |  | Hawal Salh |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Muhamad Sabri |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Gailan Rahim |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Amanj Othman |  |  |  | 2021-09-13 | 2021-09-13
|  |  | Karohk Hazem |  |  |  | 2021-09-13 | 2021-09-13

## Sheet1 (hidden)
Description | Qty.
Rain coat | 5
electric cable for lab cabin one piece 200 m | 1
Printer | 1
Torch light | 2
Fire extinguisher inspected and ready | 5
Pressure sensor | 2
Grounding Bar (Rod) | 4
Radio for communications | 5
better fly valve 6" | 3