## RN BR-04 Daily Report
Operations Integrity Management System
Document Title: SWT Daily Activity Report Document Code: OS-HOSWT-R003
[5 empty] | Rev No. V01 |  |  |  | Revision Date: 13-Sep-2015 |  |  | Page 1 of 1
6
Attention : | Mohammed Batati |  | Client : | RosNeft |  | Date : | 2021-09-14 |  |  |  | Client Logo:
From : | Hemn Majeed |  | Field : | Barda Rash |  | Run : | N/A
cc : | Ari Azad, Emad & Ibrahim F. |  | Well : | BR-04 |  | Job No : | KIU-SWT-RNHB-C-34778
OPERATION INFORMATION
|  |  | Y | N | Company | [6 empty] | Y | N
Security |  |  | Y |  | Mando |  |  | Personnel issues ? |  |  |  |  | N
Slick line /Wire line |  |  |  | N | N/A |  |  | Job Planning ? |  |  |  | Y
Servicing |  |  |  | N | N/A |  |  | Require equipment / supplies ? |  |  |  | Y
Stimulation unit |  |  | Y |  | NPS |  |  | Transport issues ? |  |  |  |  | N
DST |  |  | Y |  | NorthStar |  |  | Safety issues ? |  |  |  |  | N
Coil Tubing |  |  | N |  | N/A |  |  | Rising problems |  |  |  |  | N
Well Test |  |  | Y |  | Oilserv |  |  | Miscellaneous |  |  |  |  | N
ADDITIONAL COMMENTS ON ABOVE |  |  |  | OSCAR EVENTS |  |  | WELL TESTING DATA FROM 06:00 TO 06:00
[7 empty] | Well Name |  |  |  |  | BR-04
[7 empty] | Flowing hrs. | [6 empty] | hrs
[7 empty] | Max. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[7 empty] | Avrg. Oil Rate Last 24 Hrs. | [6 empty] | bbls/day
[7 empty] | Max. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[7 empty] | Avrg. Water Rate Last 24 Hrs. | [6 empty] | bbls/day
[7 empty] | Avrg. Gas Rate Last 24 Hrs. | [6 empty] | MMscf/d
[7 empty] | Static pressure | [6 empty] | psi
[7 empty] | Diff pressure (Barton range ) | [6 empty] | 'H2O
CMF applied
[7 empty] | Total produced oil | [6 empty] | bbls
[7 empty] | Max. H2S recorded Last 24 Hrs. | [6 empty] | %
[7 empty] | Max. CO2 recorded Last 24 Hrs. | [6 empty] | %
[7 empty] | Avrg. BSW recorded Last 24 Hrs. | [6 empty] | %
[7 empty] | MAX. WHP | [6 empty] | psi
[7 empty] | Max WHT | [6 empty] | deg C
Choke size / Pump RPM
EQUIPMENT & SPARE REQUIREMENTS | [6 empty] | COMPETITION SERVICE COMPANIES ACTIVITIES
Part No. |  | Description |  |  |  | Qty. | Serv. Company Name |  |  | Activity For last 24 Hrs.
1 |  | Grease and grease pump for the gate valves
2 |  | Coverall For Hussein Al Mezyad
3
4
5
6
7
8
9
10
11
12
CREW LIST
DAY SHIFT | [6 empty] | NIGHT SHIFT
Name |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION | Name |  |  | No of Days ON | Days on Job | OSCAR | Due Date | POSITION
Hemn Majeed | 45 | 43 | 42 |  | 2021-09-17 | Site Supervisor | Hussein Al Mezyad |  | 45 | 34 | 34 |  | 2021-09-16 | Night Supervisor
Othman Anas | 28 | 7 | 7 |  | 2021-10-06 | TDA | Nassim Jumaa |  | 35 | 38 | 38 |  | 2021-09-05 | TDA
Yassin Abdullah | 38 | 38 | 38 |  | 2021-09-05 | Chief Operator | Mohammed Nooraldeen |  | 30 | 3 | 3 |  | 2021-10-17 | Chief Operator
Shivan Kamil | 35 | 3 | 3 |  | 2021-10-10 | Operator | Rahel Mustafa |  | 35 | 38 | 38 |  | 2021-09-05 | Operator
Rebwar Jmur | 35 | 3 | 3 |  | 2021-10-10 | Operator | Salam Abdullah |  | 30 | 19 | 19 |  | 2021-09-24 | Operator
Gailan Haji | 35 | 32 | 32 |  | 2021-09-11 | BOP Specialist | Nabaz Asaad |  | 35 | 38 | 38 |  | 2021-09-05 | BOP Specialist
ACTIVITIES LAST 24 HRS
Continued circulation from tubing into casing to SWT package with brine SG 1.07.
Start POOH fishing BHA and DST string.
Performed pressure test against BOP SSV.
ACTIVITIES NEXT 24 HRS
Continue POOH fishing BHA and DST string.
RIH with DST BHA.
Prepared BY: Mohammed S. Albatati |  |  |  |  | Reviewed By: Ahmad Ullah | [5 empty] | Approved By: Jean Luc Roudil
Revision No.: V01 |  |  |  |  | Issued Date: 13-Sep-2015 | [5 empty] | Controlled Copy Online
|  | Name - Day Shift |  |  |  | Arrival Date | On location |  | Out location
|  | Hemn Majeed |  |  |  | 2021-08-03 | 2021-08-04 |  | 2021-09-17
|  | Othman Anas |  |  |  | 2021-09-08 | 2021-09-08 |  | 2021-10-06
|  | Yassin Abdullah |  |  |  | 2021-08-08 | 2021-08-08 |  | 2021-09-05
|  | Shivan Kamil |  |  |  | 2021-09-12 | 2021-09-12 |  | 2021-10-10
|  | Rebwar Jmur |  |  |  | 2021-09-12 | 2021-09-12 |  | 2021-10-10
|  | Gailan Haji |  |  |  | 2021-08-14 | 2021-08-14 |  | 2021-09-11
|  | Name - Night Shift |  |  |  | Arrival Date | On location |  | Out location
|  | Hussein Al Mezyad |  |  |  | 2021-08-12 | 2021-08-12 |  | 2021-09-16
|  | Nassim Jumaa |  |  |  | 2021-08-08 | 2021-08-08 |  | 2021-09-05
|  | Mohammed Nooraldeen |  |  |  | 2021-09-12 | 2021-09-12 |  | 2021-10-17
|  | Rahel Mustafa |  |  |  | 2021-08-08 | 2021-08-08 |  | 2021-09-05
|  | Salam Abdullah |  |  |  | 2021-08-27 | 2021-08-27 |  | 2021-09-24
|  | Nabaz Asaad |  |  |  | 2021-08-08 | 2021-08-08 |  | 2021-09-05
Formulas:
Revision Date: 13-Sep-2015 = [Date :]+45

## Sheet1 (hidden)
Description | Qty.
Rain coat | 5
electric cable for lab cabin one piece 200 m | 1
Printer | 1
Torch light | 2
Fire extinguisher inspected and ready | 5
Pressure sensor | 2
Grounding Bar (Rod) | 4
Radio for communications | 5
better fly valve 6" | 3